## Sheet1
Iteration number | Date begin | Date end | Task | Assignee | Time estimate (h) | Time taken (h) | Comments
1 | 2015-10-29 | 2015-10-31 | Research on database and choose the one to use for the project | Hakim | 3 | 3 | Done
|  |  | Identify features to be incorporated in the application | Anudeep/Manish/Yuan | 9 | 7 | Done
2 | 2015-10-31 | 2015-11-02 | Ramp-up on Dynamo DB | Hakim | 10 | 9 | Done
|  |  | Research on Python parsers, Beautiful soup and Scrapy | Anudeep | 2 | 2 | Will continue throughout the project
|  |  | Research on Python, Beautiful soup and Scrapy | Yuan | 4 |  | Will continue throughout the project
|  |  | Research on Python, Beautiful soup and Scrapy | Manish | 3 | 4 | Will continue throughout the project
3 | 2015-11-02 | 2015-11-04 | Finalize list of queries and attributes for database | Hakim | 2 | 2 | Done
|  |  | Work on the class diagram | Anudeep | 3 | 3 | Done
|  |  | Research on chart lib of python | Yuan | 2 |  | Done
|  |  | Create initial high-level architecture and class diagram for Web-crawler | Manish | 3 | 3 | Done
4 | 2015-11-04 | 2015-11-06 | Implement database table | Hakim | 3 | 4 | done: TODO ramp up on dynamodb for tests on local machine
|  |  | Implement Text parser and Url Validator | Anudeep | 2 | 2
|  |  | Research on the networkx, and draw the demo chart | Yuan | 2
|  |  | Working prototype for BFS | Manish | 4 | 6 | Done
5 | 2015-11-06 | 2015-11-08 | Meet with Yuan to confirm all the queries will be answered | Hakim/Yuan | 2 | 2 | done
|  |  | Meet with Manish to confirm the format of the data that will be sent to the database | Hakim/Manish | 2 | 1 | done
|  |  | Implement queries | Hakim | 12 | 7 | done on ddb local. Still need to undertand how to use IAM to deploy it on ddb
|  |  | Find out how to communicate with DDB table without having credentials public | Hakim | 2 | / | pushed to next iteration
|  |  | Implement Density Analysis and Word frequency | Anudeep | 4
|  |  | Implement the chart handler and draw the star char with data | Yuan | 4
|  |  | Complete initial version of BFS / DFS | Manish | 5 | 8 | Done
Comments on iteration | Hakim TODO: Update wiki for database with new design |  |  | done
6 | 2015-11-08 | 2015-11-10 | Update wiki for database | Hakim | 1 | 1 | done
|  |  | Set up IAM for secure login | Hakim | 2 | 2 | Using ddb local might be sufficient for the purposes of this project. Test at integration and adjust if need be
|  |  | Meet Yuan for integration database/ graphs | Hakim/Yuan | 1 | 1 | done
|  |  | Meet Manish for integration with data collection and tests on real database | Hakim/ Manish | 1 | 1 | done
|  |  | Implement the integrationthe between chart module and database | Yuan | 2
|  |  | Test BFS implementation with real database | Manish | 2 |  | Pending
|  |  | Integration with BFS and testing | Anudeep | 2
|  |  | Refine webcrawler | Manish | 6 | 1 | In Progress
|  |  | Integration between Webcrawler and Keyword Density Analyzer | Manish | 5 | 5 | Completed
Comments on iteration
7 | 2015-11-10 | 2015-11-12 | Test database at scale in integrated code | Hakim | 3 | 3 | done
|  |  | Find out whether it is sufficient to use ddb local or need aws version | Hakim | 2 | 2 | done
|  |  | Test the integration between database and chart module | Yuan | 3 | 2 | Done
|  |  | Meet Hakim to discuss the detail of integration | Yuan/Hakim | 2 | 1 | done
|  |  | Refine webcrawler | Manish | 8 | 4 | Done
|  |  | Integrate Webcrawler with Database | Hakim / Manish | 1 | 2 | Done
|  |  | Integrate Webcrawler with ChartHandler | Yuan / Manish | 1 | 1 | Done
Final Sprint meeting | Test integration of whole system | Manish/Yuan/Hakim/Anudeep | done
| Write script to download dependencies | Hakim | done
| Test at scale | Manish/Yuan/Hakim/Anudeep | done
| List dependencies in wiki | Hakim | done